## Instructions
FranConnect Franchise Opener Data Mapping Sample Instructions
1. Each tab in this workbook represents a different type of project checklist which can be configured within the system. A value is "Required" in every column in order for a task to be created in that Task checklist. ***Note: Only the Task Checklist tab is mandatory for initial system configuration.
2. The 'Responsibility Area' column is used to help group tasks by their Area of Responsibility, and is used for reporting purposes. (Ex. Marketing, Construction, Operations, etc.)
3. In the 'Contacts" column of each checklist you have the ability to create a "Custom Profile" instead of assigning a specific user. The 'Custom Profile' is a placeholder account which can be used to assign a task dynamically. You will be prompted to select an actual system user to assign for that 'Custom Profile' when the checklist is assigned to a new store/ location. (Example: If there are three Construction Managers to whom any project could be assigned, you would create a Custom profile titled "Construction Manager" and assign the tasks to that profile, instead of a specific user. When the checklist is assigned to a new location, you will be prompted to select a system user to apply to the Construction Manger profile for that specific location.) ***Note: The system allows a maximum of (10) Custom Profiles.
4. The 'Applicable to Store Type' column allows you to define which type of stores/locations this task is applicable for. Only those tasks applicable to that type of store will be visible when the checklist is applied to a new location, and will be dependant on what type of store the location was configured as.
5. The 'Group' column allows the client to label tasks by Groupings. The system default groupings are: High Priority, Normal Tasks, and Optional Tasks. These grouping are client specific and can be configured via the ADMIN TOOL within the system.
6. The 'Franchisee Access' column is used to set the access level to a specific task for all Franchisee Users. (Access levels are: None, View Only, or Update Status.)
7. The priority column is used to define whether the task itself is either 'Mandatory' or 'Recommended'.
8. This allows users to add a critical level to Tasks. The Critical Level Drop Down has the following options: • Critical: For a Task of high importance • Non Critical: For less important Tasks • System Item: For regular Tasks ***Note: Overdue task alerts will be sent based on the critical level of the tasks.
9. The 'Dependent On' column requires the input of a Project MileStone value. Typically the 'Opening Date' is used, however the client has the ability to configure other key milestones in the project on which specific tasks can be dependent. ***Note: The system allows a maximum of (10) custom 'Reference Dates' to be used.

## Secondary Checklists
Description | Task List, Picture Checklist, or Secondary Checklist Name | Task Description | Can be department names or simply "franchisor" and "franchisee" | Individual responsible for completion of a task. This can be a person (bob Jones) or a role (Consruction Manager). If franchisee, use "Franchise User". | Unless you have discussed alternate store types with your implementer, use 'Default Store'. | Groups help you sort tasks into chunks, either by time (Phase 1, 2, 3) or by type (Marketing, Legal), or by any other labeling system that makes sense to you. | "Franchisee Access" defines franchise user/owner access to a task. • None: Franchisee does not see the task. • View Only: Franchisee sees the task, but can't update status or complete. • Update Status: Franchisee has full access to the task. | Defines whether this task is Mandatory or Recommended. If all tasks are one or the other, choose "Recommended". | This allows for three different reminder paths that you can define: Critical, Non-Critical, and System Item. | Consult your implementer for help with complex dependencies. We recommend that you begin with all tasks related to either start of project or opening date. | If dependent on another task, choose whether dependent on Start Date, End Date, or Completion Of the other task. | List the task name upon which this task is dependent. | Enter No unless advised by your Implementer. | Enter the number of days prior to/or after the Reference Date on which this task should start. | State whether the Task should be started "Days Prior" to or "Days After" the Reference Date. For example, if the reference date is "opening date" then all tasks will be N "days prior". | Number of days after start this task should be completed. If using "days prior" this number will be SMALLER than start date, for example Start 7 days prior, finish 3 days prior for a task that takes four days. | State whether the Task should end "Days Prior" to or "Days After" the dependent task in (column 'J') or the dependent task trigger date value in (column 'K'). | List the number of days prior to the "Scheduled Start" date of the task, that you want a 'Start Task' notification to be sent to the Contact/task Owner. Note: Enter "0" to turn off reminders. | List the number of days prior to the "Scheduled Completion" date of the task, that you want a "Reminder" notification to be sent to the Contact/Task Owner. Note: Enter "0" to turn off reminders.
Field Name | [9 empty] | Task dependencies |  |  |  | Schedule Date Start |  | Schedule Date Completion |  | Send Start Reminder
| Checklist Name | Task | Responsibility Area(s) | Contact(s) | Applicable To Store Type(s) | Group | Franchisee Access | Priority | Critical Level | Dependent On | Timing trigger for task | Other Checklist task on which this task is dependent | Initialize Dependency | # of Days | Prior to or After | # of Days | Prior to or After | Send Start Reminder | Send Completion Reminder
|  | Order store sign | Construction | Construction Manager | All Stores |  | View Only | Mandatory | Critical | Opening Date | Start Date |  | Yes | 5 | Days Prior | 5 | Days Prior | 6 | 3
|  | Sign Utilities Contract | Operations | Operations Manger | Kiosk |  | Update Status | Recommended | Non-Critical | Equipment Checklist | End Date | Order Signs | No | 3 | Days After | 6 | Days After | 2 | 1
|  | Complete Lease Agreement | Real Estate | Real Estate Manager | All Stores |  | No Access | Mandatory | System Item | Task Checklist | Completion Of | Select Real Estate Broker | Yes | 4 | Days Prior | 2 | Days Prior | 1 | 1